TRINZO AI Revenue Engagement Standard Operating Procedure — Lead to Post-Delivery Success

| Version | v1.0 | Owner | Conor Flynn |
| --- | --- | --- | --- |
| Date | June 2026 | Status | Active |

Purpose & Scope

This SOP defines the end-to-end process Trinzo follows from the moment a sales lead is qualified through to post-delivery success and account expansion. It covers all five service lines — Training, Discovery Workshop, POC Factory, Partner Implementation, and Adoption Management — and is designed to be applied to engagements in the Life Sciences AI space including both GxP-regulated programmes (e.g. Medtronic, GSK) and broader AI adoption mandates.

The SOP is owned by the Head of Innovation and should be reviewed after each major programme completes to capture learnings and update guidance.

80/10/10 Rule of Thumb — Trinzo operates in the 80%: tasks where humans work better with AI. Not the 10% that is fully automated, and not the 10% that requires pure human judgment. Every engagement assessment should start with this lens.

Trinzo AI Service Lines

The five service lines below are the revenue engine for Pillar 2. Each lead should be mapped to one or more of these as early as Stage 2 (Qualification).

| Service Line | Fee (€) | What it is | Lead Time |
| --- | --- | --- | --- |
| Training | ~€30K | Bespoke AI training for teams. Role-specific, scenario-based. Scalable across a large client. | 2–4 wks |
| Discovery Workshop | ~€30K | 3-day intensive. Maps the 80/10/10 split for the client's workflows. Output: Opportunity Matrix. | 1–2 wks |
| POC Factory | ~€200K | Multiple POCs + full AI roadmap + mapped workflows. Tests tools before committing to full build. | 6–10 wks |
| Partner Implementation | €200–300K | Technical delivery of chosen solution with adoption built in. Phases: Setup → POC → Build → Pilot → Adoption. | 9–12 months |
| Adoption Management | €30K / tranche | Ongoing adoption support post-implementation. Up to 10 engagements concurrent. | Ongoing |

The Engagement Process — 8 Stages

The process runs from lead receipt through to post-delivery account expansion. Each stage has a clear trigger, defined activities, specific outputs, and a gate criterion before proceeding to the next stage.

| 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Lead Receipt | Qualify & Scope | Discovery Call | Proposal & Pricing | Contract & Kick-off | Delivery | Close & Handover | Post- Delivery |

| 01 | Lead Receipt Trigger: Sales passes a qualified lead to the AI team |
| --- | --- |

What happens at this stage

Sales identifies a prospect with an AI need and creates a handover note. The AI team (Conor) receives the lead and does an initial context check before agreeing to engage.

Activities

Receive lead handover note from Sales (client name, contact, initial pain point, any prior relationship)

Review any existing Trinzo context — past proposals, prior engagements, relevant sector knowledge

Check: is this a regulated (GxP/FDA) environment? This flags GxP consultant involvement from the start

Check: does the pain point map to an existing service line, or is it novel?

Respond to Sales within 24 hours with initial read and proposed next step

Lead Intake Checklist

| Checklist Item | Notes / Guidance |
| --- | --- |
| ☐ Client name & sector confirmed | Life Sciences sub-sector matters — pharma vs medtech vs CRO changes the GxP landscape |
| ☐ Primary contact identified | Name, title, and whether they are the budget holder |
| ☐ Initial pain point captured | In the client's own words if possible — do not paraphrase yet |
| ☐ GxP / regulated environment flagged | If yes: GxP consultant (Colm/Liam) must be in the room from Stage 3 |
| ☐ Mapped to likely service line(s) | Provisional only — confirmed in Stage 3 |
| ☐ Trinzo existing context checked | Prior proposals, related engagements, known stakeholders |
| ☐ Sales intro call or handover meeting scheduled | Within 3 working days of lead receipt |

Who owns this stage: Conor Flynn (Head of Innovation). Sales hands over but stays involved through Stage 4. If the lead is a large programme (>€150K), loop in Liam (CEO) at Stage 1.

| 02 | Qualify & Scope Trigger: Handover received, initial context checked |
| --- | --- |

What happens at this stage

Before investing time in a full discovery call, Conor does a structured qualification exercise to assess fit, likely size, and the right people to bring in. The output is a 1-page qualification note used to brief the team before Stage 3.

Qualification Questions

What is the specific pain point — and is it an AI problem or a process problem?

Who in the organisation cares about this? (Champion vs. budget holder vs. end user — they are often different people)

Is there a regulated output in scope? (GxP, FDA 820, EU MDR, ISO 13485 — these change the resourcing model significantly)

What has the client already tried or bought? (Existing Copilot, validated tools, prior failed AI projects)

What is the approximate scale? (Headcount, number of processes, geographic spread)

Is there a timeline driver? (Inspection, audit, leadership mandate, competitor pressure)

Who else are they talking to? (Awareness of competitive situation)

Service Line Mapping

Use the answers above to provisionally map the lead to a service line:

| Client Signal | Likely Service Line | Watch Out For |
| --- | --- | --- |
| "We need to train our teams on AI" | Training (€30K) | May also need a Discovery first if they haven't mapped their workflows |
| "We don't know where AI fits for us" | Discovery Workshop (€30K) | Perfect entry point — do not oversell at this stage |
| "We want to build something / test a POC" | POC Factory (€200K) | Qualify the technical environment (Azure, Microsoft 365 vs Google) |
| "We need a full AI programme / implementation" | Partner Implementation (€200–300K) | GxP requirements, regulated outputs, validation obligations |
| "We've built it but people aren't using it" | Adoption Management (€30K/tranche) | May bundle with Training — assess what was built |

Output of Stage 2

1-page Qualification Note (internal — not shared with client)

Team briefed: who attends Stage 3, what angles each person covers (Conor: AI, Jack: process, Colm/Liam: GxP if flagged)

Gate: proceed to Stage 3 only if there is a plausible fit with at least one service line

| 03 | Discovery Call Trigger: Qualification complete, team briefed, call booked |
| --- | --- |

What happens at this stage

The Discovery Call is Trinzo's most important client-facing moment before a proposal. The goal is to understand the client's world deeply enough to build a proposal that feels written for them — not templated. It is a listening exercise, not a pitch.

Discovery Call Structure (45–90 minutes)

Open — state the purpose: "We want to understand your situation before recommending anything."

Current state — what does the team do today, step by step, in practice (not the SOP)?

Pain — where is the friction, the risk, the wasted time?

AI landscape — what tools do they have, what have they tried, what does 'AI' mean to them?

GxP / regulated context — what are the compliance boundaries? What cannot be touched?

Definition of success — if this works, what does it look like in 6 months?

Timeline and budget — is there a forcing function? Has budget been approved or is this exploratory?

Discovery Call Notes Template

Record notes in real-time against these headings. Share internally within 24 hours of the call. Do not share with the client. Use verbatim client quotes wherever possible — these anchor the proposal.

| Topic | Notes |
| --- | --- |
| Current state (what they actually do) |  |
| Pain points (in their own words) |  |
| AI tools already in use |  |
| GxP / regulatory flags |  |
| Success definition |  |
| Timeline drivers |  |
| Budget signal |  |

After the Call

Write a 1-paragraph "what we heard" summary — this becomes the opening of the proposal

Confirm the right service line(s)

Identify 2–3 specific use cases to anchor the proposal

Flag any red lights: GxP complexity, unrealistic expectations, no budget signal, wrong stakeholder in the room

Gate: proceed to Stage 4 only if the picture is clear enough to write a credible proposal

| 04 | Proposal & Pricing Trigger: Discovery complete, green light to propose |
| --- | --- |

Proposal Structure

Every Trinzo proposal follows the same structure, regardless of service line. The content changes; the logic does not.

Executive Summary — what we heard, why it matters, what we're proposing (1 page max)

Background & Context — their situation, in their words, showing we listened

Our Approach — the 80/10/10 lens, DMAIC methodology where applicable, how we work

What We Will Deliver — phased plan, specific deliverables, named roles

Pricing & Commercial Terms — fees by phase/tranche, what is included/excluded

Why Trinzo — relevant experience, analogous engagements, the team

Next Steps — clear call to action, decision timeline

Pricing Guidance by Service Line

| Service Line | Fee | Duration | Key Cost Drivers | Pricing Notes |
| --- | --- | --- | --- | --- |
| Training | €30K | 2–4 wks | Conor (AI Coach) + GxP SME if regulated. Materials prep ~20h. | Scalable — large orgs may run multiple sessions. Price per cohort. |
| Discovery Workshop | €30K | 1–2 wks | Jack (DMAIC) + Conor + GxP SME if needed. ~50h total. | Often the gateway to a larger engagement. Standalone or bundled. |
| POC Factory | €200K | 6–10 wks | Sr AI Engineer (40h), Prompt Eng (40h), PM (30h), GxP Consultant if regulated (30h). | Price firmly. Scope creep is the risk — gate each POC on stakeholder sign-off. |
| Partner Implementation | €200–300K | 9–12 months | Full team: Sr AI Eng, Prompt Eng, Teams/SP Dev, GxP Consultant, PM. ~1,750h for 5 configs. | Use rolling batch model: Batch 1 includes setup; Batch 2+ cheaper as infra reused. |
| Adoption Management | €30K/tranche | Ongoing | Conor (AI coaching) + PM. Light engineering unless custom prompts needed. | Up to 10 concurrent. Price per tranche not per engagement. |

Proposal Quality Checklist

| Checklist Item | Notes / Guidance |
| --- | --- |
| ☐ Opening para quotes the client's own words | Shows you listened. If you can't do this, the discovery was not deep enough. |
| ☐ Named use cases are specific, not generic | "DIS drafter for Class II device inputs" not "AI for documentation" |
| ☐ Deliverables list is concrete and ownable | Client should be able to tell exactly what they receive at the end |
| ☐ Phasing is realistic and gated | Each phase has a clear success criterion before the next begins |
| ☐ GxP risks are explicitly addressed if applicable | Regulated clients will ask. Answer it in the proposal before they do. |
| ☐ Pricing is clear and not buried | No surprises. State what is included and what is explicitly out of scope. |
| ☐ Next steps have a clear owner and date | A proposal without a next step is a document, not a sales tool. |
| ☐ Proofread and brand-checked | All proposals go out under Trinzo brand. No errors. No generic template language left in. |

GSK Lesson: The INSPIRE proposal won because it mirrored GSK's own language ("high tool usage, variable understanding", "audit findings not yet actioned") back to them in the executive summary. Always anchor on what the client said.

| 05 | Contract & Kick-off Trigger: Proposal accepted, verbal or written go-ahead received |
| --- | --- |

Commercial & Legal

SOW drafted by PM (Kathryn) within 5 working days of go-ahead

NDA in place before any client data is shared — PM to track

Payment terms: milestone-based (at phase gate) or time-and-materials for smaller engagements

Procurement route confirmed: does the client require PO, vendor onboarding, or framework agreement? Start this immediately — procurement is always slower than expected.

Invoice schedule confirmed and logged with Finance before kickoff

Internal Kick-off (Trinzo Team)

Before the client kick-off, run a 30-minute internal briefing. This is non-negotiable.

| Checklist Item | Notes / Guidance |
| --- | --- |
| ☐ Internal team briefing pack distributed | Scope, timeline, client context, roles, key sensitivities |
| ☐ Roles and responsibilities confirmed | Who owns what deliverable. No ambiguity. |
| ☐ GxP / CSV constraints understood by all team members | If regulated: Trinzo deliverables describe human behaviours, not system internals |
| ☐ Risk register opened | At minimum: scope creep, stakeholder availability, data access, regulated output risk |
| ☐ Communication cadence agreed | Weekly status call? Fortnightly? Who attends from each side? |
| ☐ Deliverables tracker created | Live document. Updated weekly. Shared with client. |
| ☐ Conor's role in this engagement confirmed | AI Coach, AI Hub lead, or both? Hours budgeted? |

Client Kick-off

The client kick-off is the first impression of how Trinzo runs a project. It sets the tone for the entire engagement.

Introductions — names, roles, what each person contributes to this programme

Programme overview — phases, gates, timeline, key milestones

Ways of working — how we communicate, how we escalate, what the PM owns vs. what needs a joint decision

Stakeholder requirements — who from the client side is needed, when, and for what

Data and access — what Trinzo needs, by when, and from whom

First deliverable — what the client will see first, and when

Medtronic Lesson: Programme Setup (SSO, Azure tenant, data access) was 108h and the most time-sensitive phase. Always confirm IT and procurement contacts at kick-off — these are the critical path items for every technical engagement.

| 06 | Delivery Trigger: Kick-off complete, work begins |
| --- | --- |

Delivery by Service Line

The delivery model differs by service line. The following sets out the key phases, gates, and Conor's specific role in each.

Training Engagements (e.g. GSK Phase 2)

Phase 0 / Pre-engagement: Leadership Alignment session, stakeholder interviews (AI usage angle), prior audit review, prompt library scoping

Phase 1: Co-facilitate process mapping workshops (AI tool guidance), GxP boundary definition for GenAI vs Classical AI, champion identification

Phase 2: Lead all training delivery — Universal Foundation Session, Role-Specific Persona Workshops, Train-the-Auditor where applicable

Materials owned by Conor: Training decks, Prompt Libraries, Inspection Language Reference Cards, AI sections of the Playbook

Gate before delivery: all training decks reviewed by GxP SME (Colm/Liam) for regulatory accuracy

Post-training: Office Hours sessions, co-developed prompt libraries with client champions, competency checklists

Partner Implementation Engagements (e.g. Medtronic)

Use the five-phase delivery model:

| Phase | Duration | What it involves | Gate to proceed |
| --- | --- | --- | --- |
| Programme Setup | One-time upfront | Azure architecture, OpenAI baseline, regression pipeline, security review pack, IT onboarding (SSO/permissions). | IT sign-off on security pack and data processing agreement |
| POC | ~2 months | Synthetic data only. AI + prompt engineering intensive. Demonstrates core engine, dual output format, interaction model. | Stakeholder sign-off on output schema before engineering resource committed |
| Internal Build | ~2–3 months | Rebuilt in client's Azure/Microsoft tenant. Teams/SharePoint dev, GxP consultant and SOP grounding. | End-to-end test with real client data; engineer sign-off on output quality |
| Pilot | ~2 months | 3–5 named users on real work. One enthusiast, one sceptic, one average user. Prompt tuning from feedback. | Pilot users confirm meaningful time saving and reliable output |
| Adoption | ~2–3 months | SOP amendment, training, rollout, named owner handover. Tool embedded as mandatory step in at least one SOP. | Named internal owner confirmed; tool referenced in live SOP |

Weekly Delivery Rhythm

Weekly internal status: PM updates deliverables tracker, Conor reviews AI-specific tasks, flag risks early

Client status call: same day each week. PM leads. Never cancel — send written update if call must move.

Phase gate reviews: formal client meeting at each gate. Written summary circulated within 24h.

Escalation trigger: any scope change, client stakeholder change, or missed gate criterion → PM and Conor review same day

Materials quality: all training decks and playbooks reviewed by GxP SME before client delivery. No exceptions for regulated engagements.

The System-Agnostic Rule (GSK Principle): Every Trinzo deliverable describes human behaviours, decisions, and AI-assistance boundaries. Nothing we produce describes, prescribes, or depends on how any client validated system operates internally. This protects commercial scope and keeps deliverables valid regardless of client system changes.

| 07 | Close & Handover Trigger: Final deliverable accepted, programme end approaching |
| --- | --- |

What happens at this stage

The close phase is often underinvested. A strong close generates the case study, the reference, and the next engagement. A weak close leaves money and goodwill on the table.

Handover Checklist

| Checklist Item | Notes / Guidance |
| --- | --- |
| ☐ All deliverables formally accepted by client | Written sign-off, not verbal. PM to track. |
| ☐ Named internal owner confirmed at client side | Who owns the tool/process/playbook after Trinzo leaves? |
| ☐ Handover documentation complete | Prompt libraries, playbooks, training decks — all final versions in client hands |
| ☐ Usage monitoring plan agreed (if applicable) | Who checks adoption metrics? How often? What triggers a support call? |
| ☐ Final invoice issued | All milestones invoiced before final sign-off. No value left uninvoiced. |
| ☐ Extensions invoiced | If scope extended during delivery, has additional work been billed? |
| ☐ CSAT / feedback session completed | Short structured session: what worked, what could be better, NPS equivalent |
| ☐ Case study permission requested | Explicitly ask for permission to use this engagement as a case study or reference |
| ☐ Lessons learned captured internally | What would we do differently? Update this SOP. |

Value Realisation Review

Before the final client meeting, build a Value Realisation Summary: what did the client get, and how does it map to the success criteria they defined in Stage 3? This is the commercial argument for the next engagement.

State the original problem statement (from the discovery call notes)

List the deliverables produced against each phase gate

Quantify impact where possible: time saved per engineer, risk reduction, audit-readiness improvement

Name the AI use cases now embedded vs. identified but not yet built

This document is the opening slide for the Expansion conversation (Stage 8)

| 08 | Post-Delivery Success Trigger: Programme closed, client in production / adoption phase |
| --- | --- |

This is where the real revenue is

The hardest client to sell to is one who hasn't worked with you before. Post-delivery is where Trinzo compounds: expand the account, convert the case study, and move from vendor to strategic partner.

Expansion Opportunities

| Entry Point | Natural Expansion Path | Revenue Signal |
| --- | --- | --- |
| Training | Discovery Workshop — "Now you know what AI is, where should you use it?" | Medium: €30K |
| Discovery Workshop | POC Factory or Partner Implementation — "Now you know where to use it, let's build it" | High: €200K+ |
| POC Factory | Partner Implementation — selected POC moves to full build | High: €200–300K |
| Partner Implementation | Additional configurations (rolling batch model). Batch 2+ cheaper as infra reused. | Very High: recurring €1.2M+ |
| Adoption Management | Expand to additional teams, functions, or sites. | Medium: €30K/tranche |

30-60-90 Day Post-Delivery Plan

| Timing | Activity | Output |
| --- | --- | --- |
| Day 30 | Check-in call: how is adoption going? Are users encountering issues? Any prompt library gaps? | Issue log. Potential scope for additional Adoption Management tranche. |
| Day 60 | Value measurement review: are the KPIs moving? Use data to anchor the expansion conversation. | Value Realisation update. Expansion proposal trigger if warranted. |
| Day 90 | Account review: what has been built, what hasn't, what is next. Formal case study interview if permitted. | Case study draft. Expansion roadmap. Reference agreement. |

Case Study & Reference Conversion

Every completed engagement is a potential case study for Pillar 1 (Marketing Engine)

Ask for case study permission at programme close — when the client is most satisfied

Case study format: Problem → Approach → Deliverables → Measurable Outcome → Quote from stakeholder

Even without a named case study, ask for: (a) reference call consent, (b) sector/use case anonymised story, (c) LinkedIn endorsement from the primary stakeholder

Conor to write the first draft of every case study — PM to coordinate review and sign-off

Revenue Compounding: Training → Discovery → POC → Implementation → Adoption → More Configurations. The Medtronic model shows the trajectory: Batch 1 is 1,752h. Batch 2 is 1,350h. Batch 3+ is 1,200h. Every new configuration sold to an existing client is cheaper to deliver and higher margin. Protect and grow the accounts that are already in.

Quick Reference: RACI by Stage

C = Conor | J = Jack | L/C = Liam/Colm (GxP) | K = Kathryn (PM) | S = Sales

| Stage | Conor | Jack | Liam/Colm | Kathryn | Sales | Liam CEO |
| --- | --- | --- | --- | --- | --- | --- |
| 01 Lead Receipt | A/R | - | - | I | R | I (large deals) |
| 02 Qualify & Scope | A/R | C | C | I | C | I |
| 03 Discovery Call | R | R | C | S | I | C (large deals) |
| 04 Proposal | A/R | C | C | R(PM) | C | A (large deals) |
| 05 Contract/KO | R | I | I | A/R | R | A |
| 06 Delivery | R | R | R | A/R | - | I |
| 07 Close | R | I | C | A/R | I | I |
| 08 Post-Delivery | A/R | I | C | S | I | I |

R = Responsible | A = Accountable | C = Consulted | I = Informed | S = Supports

Document & Template Library

The following templates should exist as live documents in the Trinzo Drive under AI Revenue / Templates:

| Template | Purpose | Used at Stage |
| --- | --- | --- |
| Lead Intake Form | Captures client name, contact, pain point, GxP flag, service line mapping | 01 |
| Qualification Note (1-pager) | Internal brief before discovery call. Not shared with client. | 02 |
| Discovery Call Notes | Structured notes template with topic headings | 03 |
| Proposal Template | Branded, structured Trinzo proposal document | 04 |
| SOW Template | Standard Statements of Work by service line | 05 |
| Internal Team Briefing Pack | Full brief for all Trinzo team members on a new engagement | 05 |
| Deliverables Tracker | Live tracker of deliverables, owners, status, and sign-off | 06 |
| Value Realisation Summary | Pre-close document mapping outcomes to original success criteria | 07 |
| Case Study Template | Problem → Approach → Deliverables → Outcome → Quote | 08 |

Lessons Learned — From Live Engagements

From Medtronic (Partner Implementation)

Procurement and IT onboarding (SSO, Azure tenant, data access) are always the critical path. Start these at kick-off, not at Internal Build phase.

JSON output schemas must be reviewed against the client's data model before Internal Build begins. Schema misalignment discovered late is expensive.

The rolling batch model is a strong commercial argument: Batch 1 builds the infrastructure; Batch 2 reuses it. Price and pitch accordingly.

GxP consultant hours peak in Adoption, not POC. Resource planning must reflect this.

From GSK (Training + Adoption Readiness)

Mirroring the client's own language in the executive summary was the single most powerful commercial move in the proposal.

The system-agnostic principle is both a delivery protection and a commercial protection. State it explicitly in the proposal and the SOW.

Copilot usage does not mean AI literacy. Discovery revealed that 75% of users interacted with Copilot but confidence in appropriate use was low. Never assume.

Office Hours sessions during and after training delivery significantly improved adoption metrics. Build them into every training engagement.

General Principles

Free discovery time converts. Every engagement where Trinzo has done genuine discovery work before proposing has a higher win rate.

The 80% is where the revenue is. Do not chase fully automated solutions — the client doesn't need Trinzo for that. Stay in the human+AI space.

Extensions not invoiced is lost revenue. Conor to flag any scope expansion to PM same day it is identified.

The best reference is a delivered project. Every engagement close should be treated as a marketing asset.

| Trinzo AI Revenue SOP | Conor Flynn — Head of Innovation | Version 1.0 ¦ June 2026 |
| --- | --- | --- |